## Sheet1
ENGINEERING CHANGE REQUEST
PRODUCT INFORMATION | [6 empty] | ECR No: | P1012202501-01-26-26-01
Customer Name: |  | Internal |  |  |  |  | Project ID: | P1012202501
Inventory ID: |  | P1012202501 |  |  | Part Name: |  | ESP32 Stepper Controller
Drawing No: |  | P1012202501 |  |  | Drawing Revision: |  | 1
CHANGE REQUESTED
1. Expand the ground copper pours under the switching regulator ICs to better pull heat away from them. Add additional VIAs to tie to the ground plane as well. Possibly add a large copper pour on the bottom side of the PCB to better help dissipate heat. 2. Move the pluggable connectors towards the outside edges of the PCB further, around 1.5 to 2 mm should be enough. 3. Add additional test points for ESP RX/TX, stepper driver signals and temp sensor output.
REASON FOR CHANGE
1. The switching regulator ICs were power cycling due to temperature rise and not enough dissipation at the full 2A loading. 2. The connectors are difficult to remove and would look better with that change. 3. Not enough test points to help with development and testing for a dev kit.
REQUESTED BY
Name: |  | Title: |  | Date of Request: |  | Department: |  | Signature:
Mike Dawson |  | Lead Engineer |  | 2026-01-26 |  |  |  | DIGITAL
TECHNICAL EVALUATION
Can this change be done and does it provide value to the customer or company or is the change necessary for product/service operation?
It can be done and is necessary for the proper operation of the device.
REVIEWED BY
Name: |  | Title: |  | Date of Review: |  | Department: |  | Signature:
Mike Dawson |  | Lead Engineer |  | 2026-01-26 |  |  |  | DIGITAL
Approved: |  |  | Not Approved:
COMMENTS
APPROVED BY
Name: |  | Title: |  | Date of Approval: |  | Department: |  | Signature:
Mike Dawson |  | Lead Engineer |  | 2026-01-26 |  |  |  | DIGITAL
ECN INFORMATION
ECN No: | ECN-P1012202501-01-26-26-01 |  |  | ECN Date: |  | 2026-01-26
ECN Submitted by: |  | Mike Dawson